## Sheet1
| Year 1: 10/16/2016 | 2016-12-02 | 2017-02-03 | 2017-04-19 | 2017-06-02 | 2017-08-25 | Year 2: Q1 | Q2 | Q3 | Q4 | Year 3: Q1 | Q2 | Q3 | Q4
Top Priorities
Website Evaluation | Task Force 1, Process, UX Current Site Memberclicks Upgrade |  | Migrate forms, etc. to new platform. Shirley trains Board members, etc on new platform |  | Re-form TF, identify our needs and options
Uta, Sara Q, Shirley, Elsa, Crystal Trice,
Advocacy | Look at Legislative Agenda, Exec Board | Communicate with membership re: leg agenda | Get out the word about legislative day! (articles, friends, etc.) | Working on Core Values Statement |  |  | Revisit our Legislative Agenda
Leg Committee, OASL | Work with ESSA taskforce | Jane and Brooke, Stats | Contacts and updates regarding Douglas County | Prep for NLLD, postcards to reps, invited reps to OLA
Eastern/Rural Library Outreach/Support | Information gathering/talk to people re: needs, recruitment, present | [5 empty] | Form a RT? Encourage Div Status? | Revisit projects associated with this initiative
Jenny Pederson, Buzzy
Develop/Implement Targeted Member Outreach Program | Disc. at Board Meeting | Ongoing-- |  |  | Creat a suite of online trainings/webinars? Ongoing
Institutional Knowledge | [5 empty] | What do we want to save (in a repository?) | Ask for a proposal or best practices document at next meeting. Intranet? | Create an implementation plan (T.B.D.)
Past presidents, DIGOR
Next Projects
Build Broader OLA Access Opportunities for Library Support Staff |  |  |  |  | Assessment period: What is needed from the board?
Reimagine the Hotline | [6 empty] | Pending website
Branding Marketing |  |  |  |  | Assemble Fundraising Task Force |  | Pending website
Quick Strike Projects to engage members | [6 empty] | Pending website | Does this page need to be changed or moved? Membership Committee?
Build and Improve Inter-Regional Network Relationships |  |  | Start a FB book group? |  |  |  | Look at Eastern Or survey? Michele or Shirley?
Improve/assess delivery systems for Professional Development
Leadership Committee, Communications, NW Central
Establish qualitative feedback (Multiple focus groups/year) for greater insight. | Follow up with focus group partcipants from strategic planning sessions/Elsa, Jane |  |  |  | Publicize Annual Conference Evaluation Form, look at Twitter and FB Comments using the #ORLIB17 hashtag |  | Look at past surveys and decide what's relevant.
Assess and design a compelling annual professional development program offering (To include: program content, calandar, delivery mechanism, etc.) | Add Saturday Program to the conference | Calendar use, Google Calendar, and add as a widget to the OLA webpage/Communication Committee: PENDING WEBSITE | Plan and implement Leadership institute AND implement Leadership Scholarships
Note on B13: eloftis: Loot at feedback we've gotten. E. Or focus group feedback (Barratt?)