## Focus 1 - EDIAntiracism
2021 OLA Strategic Work Plan - Working Document
Actively commit to being an equitable, diverse, inclusive, and anti-racist organization
| Activities | Responsible | Support | Timing | Budget Impact | Notes
Affirm OLA’s commitment to EDI and anti-racism
| Assure units have equitable access to OLA resources and encourage better cross unit communication. | OLA Board | EDI Antiracism Committee; Public Library Division (PLD)
| Revise OLA Quarterly editorial guidelines. to better reflect EDI and anti-racist values. Provide more information about how to submit articles, actively solicit work from BIPOC authors. (Consider Librarians with Spines model) | OLA Board | OLAQ Editor
| Reinforce the revision and implementation of Antiracist policies and practices at Oregon libraries (MRJ added 3/29/21) | EDI Antiracism Committee | PLD/MRJ
Improve the diversity within OLA with recruitment, retention, and support
| EDI/Anti-Racist Committee members assist in recruit current Oregon library staff of color to be mentors within OLA program. | EDI Antiracism Committee; REFORMA-OR; Leadership Committee | Libros for Oregon (LfO)
| Work with the OLA Conference Committee to create formal guidelines and processes for soliciting and evaluating conference program proposals that use an equity lens and ensure programs on EDI topics are offered each year. Guidelines should encourage the recruitment of speakers of color. |  | Public Library Division (PLD)
| Sponsor memberships to eliminate barriers to participation on ACRL-OR Board | Academic Division
Support anti-racist libraries and library workers with educational resources
| Use OLA conference program or other hosted discussions or other events throughout year to market EDI/Anti-racist toolkit resources. |  | Public Library Division (PLD), Libros for Oregon (LfO)
| Develop TedX Talk program for Oregon library workers to share stories about their experiences with racism. | EDI Antiracism Committee
| Develop “Overdue: Weeding Out Oppression in Libraries.” podcast series | EDI Antiracism Committee

## Focus 2 - Advocacy
2021 OLA Strategic Work Plan - Working Document
Strengthen OLA’s leadership and advocacy role across the state
Provide ongoing advocacy training for the local, state, and national level
| Activities | Responsible | Support | Timing | Budget Impact | Notes
| Develop legislative agenda to help focus priorities | LDLC
| Utilize the Engage website content management tool and other communication tools for regular updates on legislative issues to OLA members | LDLC | Need Volunteer/Staffing for development
| Continue offering trainings at conferences and offer advocacy training to the wider membership (Ongoing, no OLA conference in 2022) | LDLC
| Train members in relationship building with decision makers at the local, state, and national levels | LDLC
| Host information webinars and professional development opportunities regarding Academic Freedom | Academic division
Continue to advocate for all Oregon libraries
| Create better awareness of issues in school libraries and their impact on other libraries through development of tools to help all library workers advocate in specific scenarios, such as: local school board/PTA meetings, community organizations, meetings with elected officials | OASL/LDLC
| Use more of OLA's social media outlets to amplify advocacy messages | LDLC Advocacy subgroup
More programs at OLA Conference about school library issues/needs for advocacy
| Social Media management | OASL/OLA
Build and improve inter-regional networks to support and develop emerging leaders
| Engage the Past Presidents’ Round Table to serve as advocacy "mentors". (possible to offer trainings, use them to "buddy" at legislative day) Also may want to reach out to past division chairs | OLA President; LDLC
Engage regional library groups to build leadership capacity, create a list and share regular meeting times
Identify methods to empower new members to advocate for themselves in their workplace
| Use presentation at conferences to help recruit for advocacy activities | Libros for Oregon (LfO)
| Work with other organizations outside OLA involving Oregon librarians, or library supporters, and advocacy. | Libros for Oregon (LfO)

## Focus 3 - Membership
2021 OLA Strategic Work Plan - Working Document
Increase engagement in OLA and enrich the membership experience
Build broader OLA access opportunities for all library workers
| Activities | Responsible | Support | Timing | Budget Impact | Notes
| Maximize Zoom’s potential to engage members and future members across the state with both formal and informal programming. | Shirley Roberts (with assistance) | Unit chairs/OLA Board | Ongoing | 1000 | Zoom inefficient for supporting inclusive communities (such as deaf community). We need to investigate a variety of means of access for our virtual programming & meetings.
| Make inquiries to affinity groups (e.g. library directors, rural librarians) about pertinent topics of interest in order to provide relevant resources and build enthusiasm for membership. | Membership Committee | Unit chairs/OLA Board | Ongoing |  | Identify audience and message.
| OLA units offer foundational information training for members and future members to learn more about unit focus and activities. Consider crosslines of job position responsibilities/OLA units (e.g. SSD, TSRT) Units should document activities and use OLA communication tools to amplify what is already taking place. | OLA Units | Shirley Roberts/Communications Comm | Ongoing | . | Focus on recruitment for both membership and unit/RT/committee partcipation. Need a way to express interest without expectation of stepping into leadership role. Smaller volunteer roles or opportunities within units. Potentially create informational videos about "who we are" "what we do" "how you can get involved"
| OLA assists in facilitating regional programming and social events to increase member engagement (could be in person post pandemic). Consider regional OLA liaison for libraries to help breakdown silos in rural areas and better understand local issues. | OLA Executive Board | OLA Board | Ongoing | 1000 | Virtual access may be key to this moving forward. Ties into getting information from affinity group/regional interest and relevant resources survey.
| Leverage unit scholarships as engagement and recruitment tools. | OLA Units/OLA Board | Communications Unit | Ongoing |  | Does the Communications Unit need a budget? Does OLA Communications need a full time or part time dedicated role.
| Evaluate membership dues structure. Can dues be subsidized? |  |  | Ongoing |  | Still need to determine if dues can be subsidized.
| Evaluate membership recruitment methods. | Membership Committee | Shirley Roberts/Communications | Ongoing |  | Facebook ad?
Restructure communications committee to increase volunteer engagement
| Review functions and activities of the committee to determine and define responsibilities and volunteer roles/opportunities. Consider if needs are best met in a committee structure. | OLA Executive Board | OLA Board | By Aug 2022 | 15000 | Does the Communications Unit need a budget? Does OLA Communications need a full time or part time dedicated role. It would be of immense value to have 1 individual coordinating all the responsibilities and deadlines with a committee supporting them. Board may need to come up with a 3 year sustainable plan to cover cost of this role with the goal of broadening our membership base, bringing in more sponsorship, offering more value to our members and Oregon libraries in general.
| Establish sub-units for individual communication channels (e.g. OLAQ, Hotline, social media, web site) to create focus for volunteers. | OLA Executive Board | OLA Board
| Set and articulate communication standards for OLA. Central coordination of communication activities ensures work is being done. | OLA Executive Board | OLA Board
| Evaluate how OLA uses the website to communicate prior to making any changes to web presence. | OLA Executive Board | OLA Board
Continue to provide professional development opportunities during the age of COVID
| Create professional development opportunities which provide timely content (e.g. Covid/EDI) | All units
| Engage library directors to encourage staff to participate (increases access to trainings) | Staff Training RT | State Library |  |  | STRT is is currently discussing doing a two part training about the importance and logistics of professional development/continuing education, with one part targeted at directors and the second at staff. Darci Hanning from the State Library will lead this in connection with STRT.
Better communicate the tremendous work being done by OLA in order to build value for membership.
| Strengthen mentoring programs with focus on BIPOC association members and future members. |  |  |  |  | We now have 2 separate mentoring programs for this (Leadership & EDI). May need to better define or re-evaluate.
| webinars from Academic division continue | academic division